## Worksheet
Project Phase | Budget Allocation (USD) | Scheduled Start Date | Planned End Date | Resource Utilization (%) | Current Status | Forecasted Variance
Initiation | $25,000 | Jan 1, 2024 | Jan 31, 2024 | 15% | On Track | +2%
Planning | $75,000 | Feb 1, 2024 | Mar 31, 2024 | 45% | On Track | -1%
Execution | $200,000 | Apr 1, 2024 | Sep 30, 2024 | 35% | At Risk | +8%
Monitoring & Control | $50,000 | Oct 1, 2024 | Dec 31, 2024 | 5% | Not Started | N/A
Closure | $25,000 | Jan 1, 2025 | Jan 31, 2025 | 0% | Not Started | N/A