## Worksheet
Project Name | Client Name | Month | Budget Allocation (USD) | Actual Spend (USD) | Variance (USD) | Status | Notes
Website Redesign Project | ABC Enterprises | April 2024 | 50,000.00 | 47,500.00 | +2,500.00 | On Track | Design phase completed; development underway.
Mobile App Development | TechNova Inc. | April 2024 | 120,000.00 | 112,350.00 | +7,650.00 | On Track | Backend integration completed; frontend in progress.
Marketing Campaign | Global Brands Co. | April 2024 | 35,000.00 | 38,200.00 | -3,200.00 | Over Budget | Extended ad run due to high engagement.
ERP System Implementation | MidWest Solutions | April 2024 | 90,000.00 | 85,750.00 | +4,250.00 | On Track | Training sessions scheduled; data migration complete.