## Worksheet
Week | Activity | Budget (USD) | Allocated (%) | Actual (USD) | Variance (USD) | Status
Week 1 | Project Kick-off Meeting | 500 | 10% | 480 | 20 | On Track
Week 2 | Requirements Gathering | 1500 | 30% | 1350.00+150.00 | On Track
Week 3 | Design Phase - UI/UX | 2000 | 40% | 1850.00+150.00 | On Track
Week 4 | Development Start - Backend | 3000 | 50% | 2850.00+150.00 | On Track
Week 5 | Development - Frontend Integration | 2500 | 45% | 2375.00+125.00 | On Track
Week 6 | Testing Phase (Beta) | 1800 | 35% | 1725.00+75.00 | On Track
Week 7 | Final Review & Deployment Planning | 600 | 15% | 570.00+30.00 | On Track
Total Budget |  |  | 100% | 12,675.00 | 125