## Worksheet
Month | Project Name | Status | Start Date | End Date | Budget (USD) | Actual Spend (USD) | Progress (%) | Owner | Risk Level | Next Milestone
January 2024 | Website Redesign | On Track | 2024-01-15 | 2024-03-31 | 50,000 | 38,500 | 77% | Alice Johnson | Low | Launch MVP by Feb 15
January 2024 | CRM System Upgrade | Delayed | 2024-01-10 | 2024-05-30 | 75,000 | 45,250 | 60% | Bob Smith | Moderate | Data Migration Complete by Feb 28
February 2024 | Mobile App Development | On Track | 2024-02-01 | 2024-06-30 | 150,000 | 98,750 | 66% | Cara Lee | Low | User Testing Phase by March 15
February 2024 | Marketing Campaign Rollout | Active | 2024-01-30 | 2024-04-30 | 35,000 | 28,950 | 83% | Dave Brown | Low | Analytical Review by March 10
March 2024 | Cloud Migration Project | Planning Phase | 2024-03-01 | 2024-07-31 | 120,000 | – | – | Eve Martinez | High | Detailed Plan Finalized by March 31
Monthly Project Summary - Analysis View