## Worksheet
Month | Project Name | Objective | Start Date | End Date th> | Status | Responsible Person | Key Milestones | Budget (USD) | Progress (%)
January | Website Redesign | Improve user experience and mobile responsiveness | 2024-01-01 | 2024-03-31 | In Progress | Jane Smith | UX Audit, Wireframes Approved, MVP Launch | 50,000 | 45%
February | Employee Training Program | Enhance team skills in project management tools | 2024-02-01 | 2024-03-31 | Planned | Michael Lee | Training Schedule Finalized, Sessions Scheduled | 25,000 | 10%
March | Client Onboarding System | Streamline new client registration process | 2024-03-01 | 2024-05-31 | Planned | Sarah Johnson | Requirements Finalized, Prototype Review | 75,000 | 0%
April | IT Infrastructure Upgrade | Improve network reliability and scalability | 2024-04-01 | 2024-06-30 | Planning | David Chen | Vendor Selection, Risk Assessment Complete | 150,000 | 0%
May | Product Launch (Q2) | Introduce new software feature to market | 2024-05-01 | 2024-06-30 | In Progress | Lisa Wong | Alpha Testing Complete, Marketing Campaign Ready | 120,000 | 65%
June | Quarterly Review & Optimization | Evaluate project performance and adjust strategies | 2024-06-01 | 2024-06-30 | Planned | Robert Kim | Performance Metrics Report, Strategy Update Drafted | 30,000 | 0%
July | App Analytics Integration | <Implement real-time data tracking for user behavior | 2024-07-01 | 2024-09-30 | Planning | Nina Patel | Data Model Finalized, API Setup Begins | 60,000 | 0%
August | Marketing Campaign Rollout | Launch nationwide advertising for new product | 2024-08-01 | 2024-10-31 | Scheduled | James Reed | Ad Creative Approved, Social Media Launch Plan Ready | 80,000 | 0%
September | Customer Feedback Analysis | Collect and analyze customer input for product improvements | 2024-09-01 | 2024-11-30 | Planning | Karen Taylor | Survey Distribution, Data Collection in Progress | 20,000 | 0%
October | Team Retrospective & Planning | Review processes and plan for next quarter | 2024-10-01 | 2024-11-30 | Scheduled | Alice Morgan | Retrospective Session, Action Items Documented | 5,000 | 0%
November | System Security Audit | Assess and strengthen data protection protocols | 2024-11-01 | 2024-12-31 | Planning | Tom Brooks | Vulnerability Scan, Policy Review Completed | 40,000 | 0%
December | Annual Performance Review | Assess overall project success and team performance2024-12-01 | 2024-12-31 | Planned | Emma Davis | KPI Reporting, Final Strategy Summary Drafted | 35,000 | 0%