## Worksheet
Month | Project Name | Start Date | End Date | Status | Owner | Budget (USD) | Progress (%) | Key Milestones | Next Action
January 2024 | Website Redesign | 2024-01-01 | 2024-03-31 | On Track | Alex Johnson | $50,000 | 65% | UI/UX Finalized, Development Started | Complete UI testing by 2024-02-15
January 2024 | Customer Onboarding System | 2024-01-15 | 2024-05-30 | In Progress | Sarah Chen | $75,000 | 30% | Requirement Approval, Phase 1 Design | Finalize requirements by 2024-01-31
February 2024 | Marketing Campaign Launch | 2024-02-01 | 2024-03-31 | Planned | David Miller | $35,000 | 10% | Creative Assets Ready, Strategy Finalized | Approve budget by 2024-02-14
February 2024 | HR Process Automation | 2024-02-10 | 2024-06-30 | Not Started | Lisa Wong | $90,000 | 0% | Needs Scope Review, Stakeholder Alignment | Conduct stakeholder meeting by 2024-02-28