## Worksheet
Month | Project Name | Status | Start Date | End Date th> | Budget (USD) | Actual Spend (USD) | Progress (%) | Next Milestone | Owner
January 2024 | Website Redesign | On Track | 2024-01-01 | 2024-03-31 | 50,000.00 | 38,567.25 | 77% | Launch MVP by Feb 15 | Jane Doe
January 2024 | Mobile App Development | At Risk | 2024-01-10 | 2024-06-30 | 150,000.00 | 95,342.89 | 63% | Complete login module by Feb 28 | John Smith
January 2024 | Customer Onboarding System | Planning | 2024-01-30 | 2024-11-30 | 75,000.00 | - | - | Define user journey by Feb 14 | Anna Lee
January 2024 | Data Analytics Platform | Delayed | 2024-01-05 | 2024-12-31 | 180,000.00 | 134,789.56 | 75% | Resolve integration issues by Feb 22 | Michael Brown