## Worksheet
Month | Project Name | Start Date | End Date | Status | Budget (USD) | Actual Spend (USD)%> | Progress (%) | Owner | Next Milestone
January 2024 | Website Redesign | 2024-01-15 | 2024-03-31 | In Progress | 50,000 | 32,500 | 75% | Jane Doe | Launch MVP by Feb 28
January 2024 | Mobile App Development | 2024-01-10 | 2024-06-30 | Planning | 150,000 | 18,750 | 25% | John Smith | User Research by Feb 14
February 2024 | Customer Onboarding System | 2024-02-01 | 2024-05-31 | Pending Approval | 75,000 | 9,350 | 35% | Alice Brown | Final Design Review by Feb 28
March 2024 | Marketing Campaign Launch | 2024-03-01 | 2024-04-30 | On Track | 45,000 | 41,560 | 92% | Sarah Lee | Campaign Analysis by Apr 15
April 2024 | Internal Audit Process | 2024-04-01 | 2024-05-31 | Delayed (Risk) | 30,000 | 15,675 | 52% | Michael Chen | Audit Report Submission by May 15