## Worksheet
Month | Key Project Milestones |  |  |  | Team & Resources |  |  | Status Updates
| Planned | Completed | In Progress | On Hold | Assigned Team | Resource Allocation | Risk Level th>
January | Finalize project scope document | Design phase kickoff meeting | UI wireframe approval | N/A | Development Team A | 40% allocated to UX team | Moderate (timeline risk)
February | UI/UX design finalized | Development sprint 1 complete | QA testing initiated | N/A | 60% allocated to backend team | Low (no known blockers)
March | System integration testing | Client review session scheduled | Performance optimization phase | N/A | 50% shared across QA and Dev teams | Moderate (data migration risk)
April | Full system deployment planned | Client acceptance testing ongoing | N/A | Project Management Office (PMO) | 100% resource reallocation to operations team | Low (final sign-off pending)
May | Post-deployment review conducted | Documentation finalized | N/A | N/A | Resources released to other projects | No risk identified
Note: This Extended Monthly Planner is designed for comprehensive project oversight and tracking in Project Management workflows.