## Worksheet
Month | Project Name | Owner | Start Date | End Date | Status | Progress (%) | Next Milestone | Risk Assessment
January | Website Redesign | Alex Johnson | 01/01/2024 | 03/31/2024 | On Track | 65% | UI Mockups Finalized | Low - Delay in feedback loop
February | App Development Phase 2 | Sarah Chen | 02/01/2024 | 04/30/2024 | On Track (Minor Delay) | 45% | Backend Integration Complete | Moderate - Third-party API latency
March | Customer Onboarding System | Michael Torres | 03/01/2024 | 05/31/2024 | At Risk | 15% | Initial User Testing Setup | High - Lack of user data access
April | Marketing Campaign Launch | Lisa Wong | 04/01/2024 | 05/31/2024 | On Track | 85% | Campaign Results Review | Low - Minor ad cost overrun
May | Product Feedback Analysis | David Kim | 05/01/2024 | 06/30/2024 | Planning Phase | 5% | Data Collection Begins | Low - Requires team consensus on metrics