## Worksheet
Month | Project Name | Start Date | End Date | Status | Owner | Key Milestones | Budget (USD) | Progress (%)
January 2024 | Website Redesign | 2024-01-01 | 2024-03-31 | On Track | Emma Wilson | UI Design Finalized, Development Kickoff, Launch Ready | $50,000 | 75%
February 2024 | CRM System Upgrade | 2024-02-01 | 2024-05-31 | In Progress | David Chen | Requirements Signed, Phase 1 Completed, Testing in Progress | $75,000 | 45%
March 2024 | Marketing Campaign Launch | 2024-03-01 | 2024-06-30 | Planned | Sarah Kim | Content Finalized, Media Purchased, Campaign Live in April | $30,000 | 15%
April 2024 | Team Training Program | 2024-04-01 | 2024-05-31 | Delayed | James Reed | Attendance Tracking, Workshop Schedule Set, Delivery Postponed | $20,000 | 25%