## Worksheet
Month | Project Name | Objective | Key Milestones | Responsibilities | Timeline (Start - End) | Status | Risk & Issues | Next Review Date
January | Product Launch Phase | Launch MVP with core features to market. | UI/UX finalization, beta testing completion, go-live planning. | Product Manager, Engineering Lead, QA Team | Jan 1 - Jan 31 | On Track | Minor delays in UX feedback loop. | Feb 5
February | User Feedback Integration | Implement user suggestions from beta program. | Feature updates approved, version 1.1 released. | Product Team, UX Designers, DevOps | Feb 1 - Feb 28 | On Track | No significant issues reported. | Mar 10
March | Marketing Campaign Rollout | Drive brand awareness through targeted digital campaigns. | Campaign launch, performance tracking, A/B testing. | Marketing Director, Analytics Team | Mar 1 - Mar 31 | In Progress | Initial engagement below target; content optimization needed. | Apr 5
April | Performance Optimization | Improve application speed and system reliability. | Server upgrades, load testing complete, optimization metrics reviewed. | Engineering Team, DevOps Lead | Apr 1 - Apr 30 | Planned | Depends on third-party API availability. | May 15
May | Quarterly Review & Planning | Assess performance, set goals for Q3. | Review KPIs, team feedback session, Q3 roadmap presentation. | Project Manager, Finance Representative | May 1 - May 31 | Pending | Resource allocation uncertainty. | Jun 10