## Worksheet
Project Name | Phase | Team Members | Start Date | End Date | Status | Progress (%) | Key Milestones | Budget (USD) | Risk Summary
Digital Transformation Initiative | Execution Phase | Alex Rivera, Sarah Chen, James Lee | 2024-01-15 | 2024-03-31 | On Track | 75% | User Onboarding Complete, System Integration Finalized | $320,000 | Data migration delays (low impact)
Customer Experience Upgrade | Planning Phase | Megan Park, David Thompson | 2024-02-01 | 2024-05-30 | In Progress | 45% | Requirement Gathering, UX Wireframes Approved | $180,000 | Scope creep identified (monitoring)
Mobile App Development | Design Phase | Liam Wong, Naomi Patel | 2024-01-20 | 2024-04-15 | On Track | 60% | UI/UX Design Finalized, Prototype Review Done | $250,000 | Third-party API availability (potential delay)
Cloud Infrastructure Migration | Preparation Phase | Sam Johnson, Elena Rodriguez | 2024-03-01 | 2024-06-30 | At Risk | 20% | Vendor contract negotiation, Backup strategy in place | $120,000 | Vendor delays expected; contingency plan active
Monthly Summary - March 2024 |  |  |  |  | Prepared by Project Management Office (PMO)