## Worksheet
Month | Project Name | Owner | Start Date | End Date th> | Status | Key Deliverables | Budget (USD) | Progress (%) | Next Action
January | Product Launch v2.0 | Anna Lee | 2024-01-01 | 2024-01-31 | On Track | UI/UX finalized, MVP ready | $50,000 | 85% | Finalize marketing copy by Jan 15
February | Customer Onboarding Flow | James Wang | 2024-02-01 | 2024-03-31 | In Progress | Improved onboarding steps, A/B tested | $35,000 | 45% | Conduct user testing by Feb 20
March | CRM Integration | Sarah Kim | 2024-03-01 | 2024-04-30 | Delayed (Planned) | Integrate with HubSpot, data sync complete | $60,000 | 15% | Reschedule to April 15
April | Team Training Program | Michael Reed | 2024-04-01 | 2024-05-31 | On Track | Completed 3 training sessions, feedback collected | $25,000 | 90% | Finalize training materials by April 30
May | Q2 Revenue Forecasting | Lena Torres | 2024-05-01 | 2024-05-31 | Pending Start | Revenue model analysis, key assumptions reviewed | $15,000 | 0% | Define forecast KPIs by May 5