## Worksheet
Month | Project Name | Status | Start Date | End Date | Budget (USD) | Progress (%) | Key Milestones | Risks | Owner
January 2024 | Website Redesign | On Track | 2024-01-15 | 2024-03-31 | $50,000 | 65% | UI/UX Finalized, Backend Development Start | Third-party vendor delay risk | Sarah Johnson
February 2024 | App Launch Phase 1 | In Progress | 2024-02-01 | 2024-04-30 | $75,000 | 45% | Alpha Testing Complete, Beta Release Scheduled | Server capacity issues | Mark Lee
March 2024 | Client Onboarding System | Planned | 2024-03-01 | 2024-05-31 | $40,000 | 15% | Requirements Finalized, Design Approval Pending | Client feedback timeline uncertain | Lisa Chen
April 2024 | Marketing Campaign Rollout | Not Started | 2024-04-15 | 2024-06-30 | $35,000 | 0% | Campaign Strategy Finalized, Content Drafting Phase | Content approval delay risk | David Kim