## Worksheet
Order ID | Project Name | Client Name | Start Date | End Date | Status | Assigned To | Budget (USD) | Actual Spend (USD) | Progress (%) | Priority Level | Milestones | Dependencies | Last Updated
ORD-2023-001 | Mobile App Development | TechNova Inc. | 2023-10-01 | 2024-03-31 | On Track | Sarah Johnson | 500,000 | 325,400 | 82% | High | Design Review, Beta Launch, Final Deployment | UI/UX Approval, Backend Integration | 2024-04-05
ORD-2023-002 | Cloud Migration Project | GlobalData Solutions | 2023-11-15 | 2024-06-30 | In Progress | David Lee | 750,000 | 480,250 | 63% | Medium | Data Backup, Server Setup, Security Audit | Network Upgrade, Vendor Onboarding | 2024-04-03
ORD-2023-003 | Website Redesign & SEO | EcoMart Retail | 2023-12-05 | 2024-05-15 | On Hold | Lisa Chen | 120,000 | 65,300 | 45% | Low | Content Audit, UX Testing, SEO Optimization | Marketing Campaign Approval | 2024-03-28
ORD-2023-004 | ERP System Implementation | FinCorp Holdings | 2024-01-10 | 2024-09-30 | Planned | Michael Rodriguez | 1,500,000 | - | 0% | High | Requirement Finalization, Pilot Phase, Full Rollout | Finance System Upgrade, HR Integration | 2024-04-10