## Worksheet
Order ID | Project Name | Client Name | Start Date | Due Date | Status | Priority | Assigned To | Progress (%) | Notes
ORD-2023-001 | Website Redesign | TechNova Inc. | 2023-10-01 | 2023-11-15 | On Track | Medium | Alex Rivera | 75% | Final design approval pending.
ORD-2023-002 | App Development | Innovate Solutions | 2023-10-15 | 2024-01-30 | Delayed | High | Jordan Lee | 40% | Backend integration issues.
ORD-2023-003 | Marketing Campaign | Bright Marketing Group | 2023-11-01 | 2023-12-31 | In Progress | Low | Sam Wilson | 60% | Content finalized, awaiting budget approval.
ORD-2023-004 | Product Launch | FutureEdge Co. | 2023-11-15 | 2023-12-05 | On Track | High | Taylor Chen | 90% | Pre-launch testing complete.