## Worksheet
Order ID | Project Name | Client | Start Date | End Date | Status | Assigned To | Priority | Budget (USD) | Actual Spend (USD) | Progress (%) | Next Milestone | Risk Level | Notes
ORD-2023-001 | Mobile App Development | TechNova Inc. | 2023-10-01 | 2024-03-31 | In Progress | Jane Doe | High | 250,000.00 | 185,432.50 | 68% | UI/UX Finalization (Apr 15) | Medium | Client feedback delayed due to review process.
ORD-2023-002 | Cloud Migration Project | Global Solutions Ltd. | 2023-11-15 | 2024-06-30 | On Track | John Smith | Medium | 120,000.00 | 112,345.67 | 92% | Data Backup Validation (May 31) | Low | All systems running smoothly.
ORD-2023-003 | Enterprise CRM Upgrade | FinServe Group | 2023-12-01 | 2024-05-31 | Pending Approval | Alice Brown | High | 300,000.00 | -- | 25% | Staging Environment Setup (Jan 15) | High | Awaiting final client sign-off on scope.