## Worksheet
Order ID | Project Name | Client | Start Date | End Date | Budget (USD) | Status | Actual Cost (USD) | Progress (%) | Responsible Team
ORD-2024-001 | Digital Transformation Initiative | GlobalTech Inc. | 2024-03-15 | 2024-06-30 | 750,000 | On Track | 685,250 | 85% | IT & Operations Team
ORD-2024-002 | Cloud Migration Project | DataFlow Solutions | 2024-04-01 | 2024-07-15 | 420,000 | On Track | 398,750 | 92% | DevOps Team
ORD-2024-003 | Customer Portal Upgrade | EduLink Corp. | 2024-05-10 | 2024-08-31 | 310,000 | Delayed | 295,500 | 89% | UX & Frontend Team
ORD-2024-004 | ERP System Integration | FinancePlus Group | 2024-06-15 | 2024-10-30 | 950,000 | Pending Approval | - | 25% | Finance & Systems Team