## Worksheet
Project Name | Project Manager | Start Date | End Date | Current Status | Budget (USD) | Progress (%) | Next Milestone | Responsible Team | Notes
Website Redesign | Sarah Johnson | 2023-09-01 | 2024-03-31 | On Track | $50,000 | 75% | Launch Beta Version (Feb 28) | Design & Development Team | Client feedback integrated in Phase 2.
Mobile App Development | Michael Chen | 2023-10-15 | 2024-06-30 | In Progress | $85,000 | 45% | User Testing (March 15) | Engineering & UX Team | UI mockups approved by stakeholders.
CRM System Implementation | Lisa Patel | 2023-11-01 | 2024-05-31 | Scheduled | $40,000 | 20% | Data Migration Phase (Jan 15) | IT & Operations Team | Vendor onboarding completed.
Marketing Campaign Launch | David Kim | 2023-12-01 | 2024-04-30 | Pending Approval | $35,000 | 15% | Final Review (Feb 20) | Marketing Team | Budget approval pending from finance.