## Worksheet
Order ID | Project Name | Client Name | Start Date | End Date | Status | Assigned To | Priority | Progress (%) | Notes
ORD-2023-001 | Website Redesign | ABC Corp | 2023-10-01 | 2024-03-15 | In Progress | Jane Smith | High | 75% | UI mockups approved, development in progress.
ORD-2023-002 | Mobile App Launch | XYZ Inc | 2023-11-10 | 2024-01-30 | Pending Approval | John Doe | Middle | 40% | Final QA testing scheduled for next week.
ORD-2023-003 | ERP System Upgrade | Global Solutions | 2023-12-01 | 2024-06-30 | On Hold | Lisa Chen | High | 15% | Waiting on vendor response for licensing.
ORD-2023-004 | Marketing Campaign | BrandWave | 2024-01-152024-03-31 | Scheduled | Alex Turner | Low | 0% | No content finalized yet.
Page 1 of Multi-Page Order Tracker – Project Management