## Worksheet
Order ID | Project Name | Client | Status | Assigned To | Deadline | Priority | Progress (%) | Notes
ORD-2023-001 | Website Redesign | TechFlow Inc. | On Track | Sarah Johnson | 2023-10-15 | High | 75% | UI/UX finalized, content in review
ORD-2023-002 | Mobile App Development | Global Solutions Ltd. | Pending Approval | David Chen | 2023-11-05 | Critical | 40% | Backend integration pending client feedback
ORD-2023-003 | ERP System Migration | FinanceEdge Corp. | In Progress | Lisa Wang | 2023-12-01 | Medium | 65% | Data backup completed, testing phase ongoing
ORD-2023-004 | Marketing Campaign Launch | BrightMarket Ads | On Track | Mike Thompson | 2023-10-30 | Low | 95% | Final review completed, scheduled for launch