## Worksheet
Project Name | Client | Start Date | End Date | Current Status | Assigned To | Next Milestone | Progress (%) | Dependencies | Action Items
Website Redesign | TechCorp Inc. | 2024-04-01 | 2024-05-31 | On Track | Sarah Johnson | UI/UX Approval (May 10) | 75% | Content Finalization | Review final wireframes
Mobile App Development | HealthFirst Solutions | <2024-03-15 | 2024-06-15 | In Progress | Mike Chen | Beta Testing (May 30) | 40% | Backend API Ready | Finalize payment integration
ERP System Migration | Global Logistics Group | 2024-04-10 | 2024-07-15 | Pending Approval | Linda Patel | Staging Review (May 15) | 20% | Security Audit Completed | Obtain CFO approval
Marketing Campaign Launch | BrightMedia Co. | 2024-05-01 | 2024-05-31 | Ready to Start | David Kim | Approval from Sales (May 5) | 0% | Budget Finalized | Submit creative assets