## Worksheet
Task | Responsible Person | Start Date | End Date | Status | Budget Allocation ($) | Progress (%) | Notes
Project Initiation & Planning | Jane Smith | 2024-03-01 | 2024-03-15 | In Progress | 15,000 | 60% | Finalize scope and deliverables.
Team Recruitment & Onboarding | Alex Chen | 2024-03-16 | 2024-04-05 | Not Started | 8,500 | 0% | Hire three key staff members.
Budget Finalization & Approval | Maria Lopez | 2024-03-20 | 2024-03-31 | Completed | 25,000 | 100% | Approved by CFO.
System Development & Testing | David Kim | 2024-04-06 | 2024-05-30 | Not Started | 75,000 | 0% | Build and test core modules.
Training & User Onboarding | Sophia Reed | 2024-06-01 | 2024-06-15 | Not Started | 15,000 | 0% | Conduct training sessions for staff.