## Worksheet
Project Name | Project Code | Start Date | End Date | Budget (USD) | Current Status | Responsible Manager | Team Size | Next Milestone
Client Onboarding Initiative | PJM-001 | 2024-03-01 | 2024-06-30 | 150,000 | On Track | Jane Smith | 8 | Q2 Delivery Review
Digital Transformation Project | PJM-002 | 2024-04-15 | 2025-12-31 | 750,000 | In Progress | Michael Brown | 12 | Phase 3 Completion (Q3)
Marketing Campaign Launch | PJM-003 | 2024-05-01 | 2024-11-30 | 85,000 | Planning Phase | Sarah Lee | 5 | Budget Approval (May 15)
Product Development Phase 2 | PJM-004 | 2024-06-10 | 2025-03-31 | 1,200,000 | Pending Approval | David Chen | 15 | Prototype Review (July 20)