## Worksheet
Task | Description | Responsible Person | Start Date | End Date | Status | Budget Allocation (USD) | Actual Spend (USD) | Remaining Budget (USD) | Progress (%)
Project Planning | Define project scope, objectives, and deliverables. | John Smith | 2024-03-01 | 2024-03-15 | Completed | 5,000.00 | 4,850.00 | 150 | 97%
Requirements Gathering | Collect stakeholder needs and technical requirements. | Sarah Lee | 2024-03-16 | 2024-04-10 | In Progress | 7,500.00 | 3,200.00 | 4,300.00 | 42%
Design Phase | Create system architecture and UI mockups. | Mike Johnson | 2024-04-11 | 2024-05-05 | Not Started | 12,000.00 | 0 | 12,000.00 | 0%
Development | Build core modules and integrate components. | Team A | 2024-05-06 | 2024-07-15 | Not Started | 35,000.00 | 0 | 35,000.00 | 0%
Testing & Quality Assurance | Conduct unit, integration, and user testing. | Lisa Chen | 2024-07-16 | 2024-08-30 | Not Started | 18,500.00 | 0 | 18,500.00 | 0%
Deployment & Go-Live | Release to production environment and monitor. | DevOps Team | 2024-09-01 | 2024-09-15 | Not Started | 6,800.00 | 0 | 6,800.00 | 0%
Post-Implementation Review | Evaluate project success and gather feedback. | Project Manager | 2024-09-16 | 2024-10-31 | Not Started | 3,500.00 | 0 | 3,500.00 | 0%
Total Budget |  |  |  | $88,300.00 | Actual Spend |  |  | $8,050.00