## Worksheet
Task | Assigned To | Start Date | End Date | Status | Budget (USD) | Actual Spend (USD) | Progress (%) | Responsible Team | Dependencies
Project Planning & Scope Definition | John Smith | 2024-03-01 | 2024-03-15 | Completed | 10,000 | 9,800 | 100% | Project Management Team | -
Resource Allocation & Team Formation | Lisa Chen | 2024-03-16 | 2024-04-05 | In Progress | 8,500 | 4,200 | 50% | HR & Operations Team | Project Planning Phase
Requirement Gathering Workshops | Mark Johnson | 2024-04-06 | 2024-04-18 | Planned | 12,000 | - | - | Product & UX Team | Design Finalization
Risk Assessment & Mitigation Strategy | Sarah Williams | 2024-04-19 | 2024-05-03 | Pending | 6,000 | - | - | Risk Management Team | Requirement Finalization
Development & Sprint Execution | Team A | 2024-05-04 | 2024-08-31 | Not Started | 150,000 | - | - | Development Team | Requirements Approved