## Worksheet
Task | Assigned To | Start Date | End Date | Status | Progress (%)
Project Planning | Jane Doe | 2024-03-01 | 2024-03-15 | In Progress | 65%
Resource Allocation | John Smith | 2024-03-16 | 2024-03-30 | Pending | 0%
Design Phase | Lisa Chen | 2024-04-01 | 2024-04-30 | Not Started | 0%
Development Phase | Marcus Lee | 2024-05-01 | 2024-06-30 | Not Started | 0%
Testing & QA | Sophia Kim | 2024-07-01 | 2024-07-31 | Not Started | 0%