## Worksheet
Task | Assigned To | Due Date | Status | Priority | Estimated Hours | Actual Hours
Project Kickoff Meeting | John Doe | 2024-04-01 | Completed | High | 8 | 8
Requirement Gathering | Jane Smith | 2024-04-10 | In Progress | High | 16 | 6
Design Finalization | Mike Johnson | 2024-04-25 | Not Started | Medium | 20
Development Phase | Team A | 2024-05-15 | Not Started | High | 80
Testing & Quality Assurance | Sarah Lee | 2024-06-01 | Not Started | Medium | 30
Client Presentation | John Doe | 2024-06-15 | Not Started | High | 10