## Worksheet
Date | Task | Assignee | Status | Priority | Estimated Hours | Actual Hours | Deadline | Progress (%)
2024-04-01 | Project Kickoff Meeting | John Doe | Completed | High | 2 | 2 | 2024-04-01 | 100%
2024-04-05 | Requirements Gathering | Jane Smith | In Progress | High | 8 | 4.5 | 2024-04-10 | 56%
2024-04-12 | Design Phase Review | Mike Johnson | Pending | Medium | 6 | 0 | 2024-04-15 | 0%
2024-04-18 | Development Start | Team A | Not Started | High | 12 | 0 | 2024-05-10 | 0%