## Worksheet
Project Phase | Objective | Key Activities | Timeline (Start - End) | Responsible Person | Milestones | Risk Assessment | Status
Initiation | Define project scope, objectives, and feasibility. | Feasibility study, stakeholder analysis, charter development. | 2024-01-01 - 2024-01-31 | Peter Johnson | Approval of project charter | Low risk – clear stakeholder alignment | Completed
Planning | Develop detailed project plan and resource allocation. | Work breakdown structure (WBS), schedule, budget, risk register. | 2024-02-01 - 2024-03-15 | Sarah Lee | Finalized WBS and schedule approval | Moderate risk – dependencies on vendor timelines | In Progress
Execution | Implement project deliverables according to plan. | Team setup, task assignment, deliverable creation. | 2024-04-01 - 2024-08-31 | Mark Thompson | First prototype delivery (Q3) | High risk – scope creep potential | Pending Review
Monitoring & Control | Track progress, manage changes, and ensure quality. | Performance reviews, change requests, quality checks. | 2024-05-01 - 2024-10-31 | Lisa Chen | Monthly status reports and audits | Moderate risk – budget overruns possible | Active
Closure | Finalize all deliverables, document outcomes, and close project. | Final review, lessons learned, client sign-off. | 2024-11-01 - 2024-11-30 | Peter Johnson | Project handover and closure report | Low risk – formal review complete | Not Started