## Worksheet
Task | Assignee | Start Date | End Date | Status | Priority
Project Kickoff Meeting | John Doe | 2024-03-01 | 2024-03-01 | Completed | High
Requirements Gathering | Jane Smith | 2024-03-02 | 2024-03-15 | In Progress | High
Design Phase | Mike Johnson | 2024-03-16 | 2024-03-31 | Not Started | Medium
Development Sprint 1 | Sarah Lee | 2024-04-01 | 2024-04-15 | Not Started | High
Testing & QA | David Kim | 2024-04-16 | 2024-05-05 | Not Started | Low
Project Review & Closeout | All Team Members | 2024-05-06 | 2024-05-06 | Not Started | High