## Worksheet
Project Name | Start Date | End Date | Status | Owner | Budget (USD) | Progress (%) | Next Milestone
Website Redesign | 2024-03-15 | 2024-06-30 | On Track | Sarah Johnson | $150,000 | 75% | UI/UX Final Approval
Mobile App Development | 2024-04-01 | 2024-09-30 | Planning | Mike Chen | $300,000 | 25% | Requirement Finalization
Customer Onboarding Platform | 2024-05-10 | 2024-11-15 | In Progress | Lisa Wong | $200,000 | 50% | Beta Testing Launch
Marketing Campaign 2024 | 2024-06-01 | 2024-08-31 | Completed | David Ruiz | $75,000 | 100% | Post-Campaign Review