## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Priority | Progress (%)
Project Initiation | 2024-03-01 | 2024-03-15 | John Smith | Completed | High | 100%
Requirements Gathering | 2024-03-16 | 2024-04-10 | Sarah Johnson | In Progress | Medium | 65%
Design Phase | 2024-04-11 | 2024-05-15 | Mike Davis | Not Started | High | 0%
Development Phase | 2024-05-16 | 2024-07-30 | Emma Lee | Planned | Medium | 0%
Testing & Quality Assurance | 2024-08-01 | 2024-09-15 | David Brown | Not Started | High | 0%
Deployment & Launch | 2024-09-16 | 2024-09-30 | Lisa Wong | Planned | Medium | 0%