## Worksheet
Project Phase | Start Date | End Date | Responsible Person | Key Deliverables | Status
Idea & Feasibility | 01/04/2024 | 05/04/2024 | Alex Rivera | Market analysis, MVP concept | In Progress
Product Design | 06/04/2024 | 15/05/2024 | Sam Chen | Wireframes, UI mockups | Planned
Development | 16/05/2024 | 30/07/2024 | Jordan Lee | Frontend, Backend, APIs | Not Started
Testing & QA | 01/08/2024 | 15/08/2024 | Taylor Kim | Bug fixes, User testing | Scheduled
Launch & Post-Launch | 16/08/2024 | 31/08/2024 | Morgan White | Go-live, Analytics setup | Pending Approval