## Worksheet
Task | Assigned To | Start Date | End Date | Status | Progress (%) | Priority | Dependencies | Notes
Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | Completed | 100 | High |  | All stakeholders aligned on goals.
Requirements Gathering | Jane Smith | 2024-04-02 | 2024-04-15 | In Progress | 65 | High | Kickoff Meeting | Collecting user needs and functional specs.
Design Phase | Alex Brown | 2024-04-16 | 2024-05-10 | Not Started | 0 | Medium | Requirements Gathering | Create wireframes and UI mockups.
Development Phase | Team A | 2024-05-11 | 2024-07-30 | Not Started | 0 | High | Design Phase | Build core application modules.
Testing & QA | Lisa Chen | 2024-08-01 | 2024-08-31 | Not Started | 0 | High | Development Phase | Conduct functional and regression testing.
Go-Live & Training | Mark Taylor | 2024-09-01 | 2024-09-15 | Not Started | 0 | Medium | Testing & QA | Deploy system and train end-users.