## Worksheet
Project Name | Phase | Budget (USD) | Actual Spend (USD) | Variance (USD) | % of Budget Used | Status | Next Milestone
Digital Transformation Initiative | Planning & Design | 500,000 | 325,000 | +175,000 (Under Budget) | 65% | On Track | Q3 2024
Customer Engagement Platform | Development | 800,000 | 640,000 | +160,000 (Under Budget) | 80% | On Track | Mid-October 2024
Supply Chain Optimization | Implementation | 1,200,000 | 980,000 | +220,000 (Under Budget) | 81.7% | On Track | Q4 2024
Marketing Automation Suite | Testing & QA | 350,000 | 285,000 | +65,000 (Under Budget) | 81.4% | On Track | Early November 2024