## Worksheet
Project Name | Project Manager | Start Date | End Date | Budget (USD) | Actual Spend (USD)> | Remaining Budget (USD) | Cost Variance | Schedule Variance | Earned Value (EV) | Planned Value (PV) | Actual Cost (AC) | Schedule Performance Index (SPI) | Cost Performance Index (CPI) | Forecast at Completion (EAC) | Variance Analysis | Risk Register Status | Milestones Achieved | Resource Allocation | Key Deliverables
Product Launch 2024 | Jane Doe | 2024-03-01 | 2024-07-31 | $500,000 | $425,600 | $74,400 | -$74,400 | +$15,200 | $385,600 | $410,000 | $425,600 | 1.03 | 0.99 | $537,826 | On track with minor cost overrun; schedule ahead of plan. | Active (3 risks mitigated) | Milestone 1, 3, 5 completed | Team A + External Vendor | Beta Release, Marketing Campaign
Customer Portal Redesign | John Smith | 2024-04-15 | 2024-10-30 | $350,000 | $318,950 | $31,050 | -$31,050 | +$22,400 | $348,675 | $350,000 | $318,950 | 1.08 | 1.04 | $356,422 | Under budget; schedule on track. | Active (1 risk open) | Milestone 2, 4 completed | Team B + UX Design Studio | User Onboarding Flow, Admin Panel
Cloud Migration Project | Lisa Chen | 2024-05-01 | 2024-12-31 | $600,000 | $598,750 | $1,250 | -$1,250 | +$34,200 | $589,600 | $615,000 | $598,750 | 1.02 | 1.01 | $643,273 | Excellent cost control; schedule ahead of plan. | Closed (all risks resolved) | All milestones achieved | Team C + Cloud Engineers | Data Transfer, Backup System, Security Audit