## Worksheet
Project Name | Start Date | End Date | Budget (USD) | Actual Spend (USD) | Profit/Loss (USD) | Status | Progress % | Owner | Next Milestone
Product Launch 2024 | 2024-03-01 | 2024-06-30 | 500,000.00 | 425,678.50 | +74,321.50 | On Track | 82% | Sarah Johnson | Q2 User Testing Completion
Mobile App Redesign | 2024-04-15 | 2024-09-30 | 350,000.00 | 312,895.75 | +37,104.25 | On Track | 68% | Mike Chen | UI/UX Final Review
Customer Onboarding System | 2024-05-01 | 2024-11-30 | 600,000.00 | 587,234.56 | +12,765.44 | On Track | 75% | Lisa Martinez | Pilot Launch in Q3
Marketing Automation Upgrade | 2024-06-10 | 2024-12-31 | 200,000.00 | 198,543.21 | +1,456.79 | On Track | 50% | David Kim | Integration with CRM