## Worksheet
Project Name | Start Date | End Date | Budget (USD) | Actual Spend (USD) | Remaining Budget (USD) | Progress (%) | Status | Next Milestone
Phase I Development | 2024-01-15 | 2024-06-30 | $500,000 | $385,200 | $114,800 | 77% | On Track | UI/UX Finalization (June 15)
Marketing Launch | 2024-03-01 | 2024-09-30 | $250,000 | $198,750 | $51,250 | 79% | On Track | Campaign Rollout (May 10)
Operations Deployment | 2024-07-01 | 2024-12-31 | $750,000 | $632,400 | $117,600 | 84% | On Track | System Go-Live (September 30)
Post-Launch Support | 2024-10-01 | 2025-03-31 | $150,000 | $98,450 | $51,550 | 66% | Planned | Customer Training (November 15)