## Worksheet
Project Name | Objective | Start Date | End Date | Owner | Budget (USD) | Status | Key Milestones | Risk Assessment | Dependencies
Annual Product Development | Develop and launch a new product line aligned with annual business goals. | 01/01/2024 | 12/31/2024 | Jane Smith | $500,000 | On Track | Product Design Review (03/15) Prototype Approval (06/30) Market Launch (12/01) | Medium – Delay in supplier delivery | R&D team completion, Marketing campaign approval
Annual IT Infrastructure Upgrade | Upgrade core systems to support increased user capacity and security standards. | 03/01/2024 | 09/30/2024 | Mark Johnson | $750,000 | In Progress | System Assessment (04/05) Security Audit (07/10) Go-Live (09/25) | High – Potential downtime during transition | Network team, Data backup operations
Annual Customer Experience Initiative | Improve customer satisfaction through service redesign and feedback integration. | 05/01/2024 | 11/30/2024 | Lisa Chen | $300,000 | Planned | Customer Survey Launch (05/30) Service Workflow Redesign (08/15) Feedback Implementation Review (10/31) | Low – Minor staff training delays | Customer support team, HR
Annual Training & Development Program | Enhance workforce skills through targeted training and certification programs. | 06/01/2024 | 06/30/2024 | David Park | $150,000 | On Track | Needs Assessment (06/05) Course Delivery (06/15) Completion & Evaluation (06/28) | Low – Limited participation in some departments | HR department, Department Heads