## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Notes
Project Initiation | John Smith | 2024-01-15 | 2024-01-25 | Completed | 100% | Feasibility study and stakeholder approval completed.
Scope Definition | Maria Garcia | 2024-01-26 | 2024-02-10 | In Progress | 75% | Final scope document under review.
Resource Planning | David Lee | 2024-02-11 | 2024-02-28 | Not Started | 0% | Team assignments and budget estimates pending.
Risk Assessment | Sarah Kim | 2024-03-01 | 2024-03-15 | Not Started | 0% | Identify and prioritize potential risks.
Project Execution | Team Lead | 2024-03-16 | 2024-06-30 | Not Started | 0% | Main development and delivery phase.