## Worksheet
Task | Responsible | Start Date | End Date | Duration | Status | Dependencies | Notes/Remarks
Project Initiation | Project Manager | 2024-01-01 | 2024-01-15 | 15 days | In Progress | - | Define project scope, objectives, and stakeholders.
Feasibility Study | Business Analyst | 2024-01-16 | 2024-01-31 | 25 days | Not Started | Project Initiation Complete | Assess technical, financial, and operational feasibility.
Requirements Gathering | Requirements Team | 2024-02-01 | 2024-03-15 | 65 days | Not Started | Feasibility Study Approved | Interview stakeholders and document functional and non-functional requirements.
Design Phase | UX/UI Designer & Architects | 2024-03-16 | 2024-05-10 | 65 days | Not Started | Requirements Finalized | Develop wireframes, user flows, and system architecture.
Development | Development Team | 2024-05-11 | 2024-08-31 | 120 days | Not Started | Design Approved | Implement features based on approved design and requirements.
Testing & Quality Assurance | QA Team | 2024-09-01 | 2024-10-15 | 65 days | Not Started | Development Complete | Conduct unit, integration, and user acceptance testing.
Deployment | Operations & DevOps | 2024-10-16 | 2024-10-20 | 5 days | Not Started | Testing Complete & Signed Off | Deploy to production environment with rollback plan.
Post-Deployment Review | Project Manager | 2024-10-21 | 2024-10-25 | 5 days | Not Started | Deployment Complete | Collect feedback, document lessons learned, and close project phases.