## Worksheet
Task | Owner | Start Date | End Date | Duration | Status | Dependencies | Progress (%)
Project Initiation | John Smith | 2024-03-15 | 2024-03-20 | 5 days | Completed | - | 100%
Scope Definition | Emily Davis | 2024-03-21 | 2024-03-28 | 7 days | In Progress | Project Initiation | 65%
Resource Allocation | Michael Brown | 2024-03-29 | 2024-04-05 | 7 days | Not Started | Scope Definition | 0%
Risk Assessment | Sarah Lee | 2024-04-06 | 2024-04-12 | 7 days | Not Started | Scope Definition | 0%
Project Planning | David Kim | 2024-04-13 | 2024-04-25 | 13 days | Not Started | Resource Allocation, Risk Assessment | 0%
Milestone Review | Team Lead | 2024-04-26 | 2024-04-30 | 5 days | Not Started | Project Planning | 0%