## Worksheet
Task | Responsible Person | Start Date | End Date | Status | Priority | Dependencies
Project Initiation | Project Manager | 2024-03-01 | 2024-03-15 | Completed | High | N/A
Requirements Gathering | Business Analysts | 2024-03-16 | 2024-04-10 | In Progress | High | Project Initiation
Design Phase | Design Team | 2024-04-11 | 2024-05-05 | Pending | Middle | Requirements Gathering
Development Phase | Development Team | 2024-05-06 | 2024-07-31 | Pending | High | Design Phase
Testing & Quality Assurance | QA Team | 2024-08-01 | 2024-08-31 | Pending | High | Development Phase
Deployment & Launch | IT Operations Team | 2024-09-01 | 2024-09-15 | Pending | Middle | Testing & Quality Assurance
Post-Launch Review & Feedback | Project Manager, Stakeholders | 2024-09-16 | 2024-09-30 | Pending | Middle | Deployment & Launch