## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Status | Priority
Project Initiation | John Smith | 2024-01-15 | 2024-01-18 | 4 | Planned | High
Scope Definition | Sarah Lee | 2024-01-19 | 2024-01-25 | 7 | In Progress | High
Stakeholder Analysis | Mike Johnson | 2024-01-26 | 2024-01-30 | 5 | Planned | Medium
Risk Assessment | Lisa Wong | 2024-02-01 | 2024-02-05 | 5 | Not Started | High
Resource Allocation | Tom Brown | 2024-02-06 | 2024-02-10 | 5 | Planned | Medium
Project Execution Phase | Team Lead | 2024-02-11 | 2024-03-31 | 60 | Not Started | High