## Project Plan Template
Project Plan - Simple Style
Task | Responsible Person | Start Date | End Date | Status | Priority
Project Initiation | Project Manager | 2024-01-15 | 2024-01-20 | In Progress | High
Requirements Gathering | Business Analyst | 2024-01-21 | 2024-01-30 | Pending | High
Design Phase | UI/UX Designer | 2024-02-01 | 2024-02-15 | Not Started | Moderate
Development Phase | Software Developer Team | 2024-03-01 | 2024-05-31 | Not Started | High
Testing & Quality Assurance | QA Engineer | 2024-06-01 | 2024-06-30 | Not Started | Moderate
Deployment & Launch | Operations Team | 2024-07-012024-07-15 | Not Started | High