## Worksheet
Project Name | Week Starting | Objective | Key Activities | Responsible Person | Milestones | Status (Progress %) | Risks & Issues | Next Week Actions
Website Redesign | 2023-10-01 | Improve user experience and site performance. | UI/UX research, wireframing, content audit. | Sarah Chen | Finalize wireframes by Week 2 | 70% | Limited access to client design assets. | Complete content audit and obtain final approvals.
Product Launch | 2023-10-08 | Launch new mobile app in beta phase. | Beta testing, user feedback collection, bug fixes. | James Rivera | App available to 1000 users by Week 3 | 45% | High user drop-off rate in first session. | Optimize onboarding flow and improve load time.
Marketing Campaign | 2023-10-15 | Increase brand awareness through social media. | Create content calendar, run ads, track engagement. | Lena Patel | Reach 50K impressions by Week 2 | 60% | Ad budget exceeded in Week 1. | Reallocate budget to high-performing channels.