## Worksheet
Task ID | Task Name | Owner | Start Date | End Date th> | Status | Progress (%) | Dependencies | Priority | Risk Level
PMT-001 | Project Initiation & Planning | John Smith | 2024-01-15 | 2024-02-15 | In Progress | 75% | Task PMT-003, PMT-004 | High | Medium
PMT-002 | Resource Allocation & Scheduling | Sarah Lee | 2024-01-20 | 2024-03-15 | Pending Approval | 30% | Task PMT-001, PMT-005 | Medium | Low
PMT-003 | Requirement Gathering Workshop | Mike Johnson | 2024-02-01 | 2024-02-10 | Completed | 100% | None | Low | None
PMT-004 | Stakeholder Engagement Plan | Lisa Wong | 2024-01-30 | 2024-03-31 | In Progress | 55% | Task PMT-001, PMT-006 | High | Medium
PMT-005 | Scope Validation Meeting | David Kim | 2024-03-10 | 2024-03-25 | Pending Approval | 15% | Task PMT-002, PMT-010 | Medium | Low