## Worksheet
Project Name | Team Member | Task Description | Assigned Date | Due Date | Status | Progress (%) | Remarks
Website Redesign Project | Sarah Chen | Design new user interface and wireframes | 2023-10-03 | 2023-10-15 | In Progress | 65% | Feedback from stakeholders due next week
Mobile App Development | David Kim | Develop authentication module | 2023-10-04 | 2023-10-20 | On Track | 85% | Testing scheduled for 10/18
Marketing Campaign Launch | Lena Patel | Create social media content calendar | 2023-10-05 | 2023-10-17 | Completed | 100% | Campaign live on social platforms
Customer Support System Upgrade | Michael Torres | Implement new ticketing system | 2023-10-06 | 2023-10-25 | Pending Approval | 30% | Awaiting budget sign-off from finance